## START HERE
ServiceNow Architecture Discovery Workbook
Purpose | Learn an inherited ServiceNow instance by tracing real work, record what you can PROVE, and make unknowns and risks visible - with limited access. Companion to the Obsidian vault (same IDs, same vocabulary).
PRINCIPLES
ServiceNow is authoritative | If this workbook disagrees with the platform, the platform wins until you resolve the difference. Update the workbook, set Last Reviewed.
Never guess | If you don't know why something exists, log it on the Unknowns sheet. Write 'UNKNOWN' in Purpose columns. Do not invent reasons.
Document relationships | A table name is less useful than knowing what depends on it. Use the Dependencies sheet and Impact Check.
Business purpose first | Link objects to a Business Process. If you cannot, say so.
Track ownership and confidence | Every Critical/High object should end with an owner. Every row has a Confidence level (High=verified, Medium=strongly supported, Low=inferred).
Capture why | Record decisions (and reconstructed decisions, labeled as such).
Build incrementally | Do not try to document the whole platform. Document what you encounter while tracing real processes.
HOW TO USE (daily loop)
1. Architecture Overview | Fill what you can verify. Everything else becomes an Unknown.
2. Inventory | Add rows to Object Inventory (existence + owner + criticality) and Applications.
3. Pick processes | Business Processes sheet: choose 3-5, set Priority to Trace.
4. Trace end-to-end | User -> catalog -> variables -> flow -> tables -> scripts -> notifications -> approvals -> integrations -> reporting.
5. Document as you meet objects | Use the detail sheet for the type (Tables, Flows, ...). Add an Object Inventory row for each.
6. Record relationships | Dependencies sheet: Source -> relationship -> Target. Use exact object names.
7. Record Unknowns and Risks | Never leave a question in your head. Set Access Needed - that builds your access case.
8. Validate with SMEs | Set Confidence to High only when verified directly. Record who validated and when.
9. Check the Dashboard | See coverage, owner gaps, critical risks. Update Current Focus.
10. Before any change | Use Impact Check, then Decisions and Change History.
SHEET MAP
Dashboard | Metrics (formulas)
Architecture Overview | Instance facts, people, layers
Object Inventory | Master list of everything important
Applications / Tables / Fields | Application and data model
Catalog Items / Variables | Service catalog
Flows / Scripts & Rules | Automation and code
Integrations | External connections
Security | Roles, groups, ACLs
Business Processes | The spine - start here for tracing
Dependencies / Impact Check | Relationships and 'what breaks if I change this?'
Risks / Unknowns | Risk register (auto score) and unknowns register
Decisions / Change History | The 'why' and what changed
30-Day Plan | Day-by-day plan
Access Matrix / Access Roadmap | What needs what; what to request as responsibilities grow
Responsibility Modes / Transition Checklist | Protection from ownership without authority
Reference Lists | Dropdown values and definitions
LEGEND
Yellow + italic rows | FICTIONAL EXAMPLES (IDs start EX-). They show how to fill a row. Not your environment. Excluded from Dashboard.
Yellow input cells | Cells you edit on Dashboard / Impact Check.
Grey/blue header | Hover headers with a red triangle for tips.
Rows 'Suspected' on Risks | Hypotheses to check, not findings.
ASSUMPTIONS (mine, not facts about your instance)
- | ServiceNow role names, ACLs and table access differ by instance. 'Typical access' text is a starting hypothesis; record the real role in Notes.
- | Examples (EX-...) are invented: no real configuration of yours is represented.
- | Table, field and menu names mentioned are common ServiceNow conventions; confirm in your instance.
- | Seeded Unknowns/Risks are common to inherited instances; only R-001/R-002 are stated facts from you.
- | Do not run background scripts or change production without authority; this workbook is for read-only discovery until your transition agreement says otherwise.

## Dashboard
ARCHITECTURE DASHBOARD - all values are formulas. Yellow cells are yours to edit. Example rows (IDs starting EX-) are excluded.
FOCUS (edit)
Current discovery focus | (e.g., Process 1: ...)
Next discovery target | (e.g., ...)
30-day plan days done | 0 / 30
INVENTORY & COVERAGE
Metric | Discovered | Documented | % Documented
Total objects (Object Inventory) | 0 | 0 | 0%
Tables | 0 | 0 | 0%
Flows / Subflows | 0 | 0 | 0%
Catalog items | 0 | 0 | 0%
Integrations | 0 | 0 | 0%
Business processes | 0 | 0 | 0%
Scripts & rules | 0 | 0 | 0%
Security (roles/groups/ACLs) | 0 | 0 | 0%
Applications | 0 | 0 | 0%
Fields (tracked) | 0 | 0 | 0%
Variables (tracked) | 0 | 0 | 0%
OVERALL DOCUMENTATION % (Object Inventory) |  |  | 0%
RISKS & UNKNOWNS (open items only)
Critical risks | 1
High risks | 1
Suspected risks still to verify | 16
Critical unknowns (unresolved) | 6
High unknowns (unresolved) | 5
All unresolved unknowns | 12
Unknowns blocked by access | 0 |  |  |  | Use these to justify access requests
OWNERSHIP & CUSTOMIZATION (Object Inventory)
Undocumented customizations (Custom or Customized OOTB, not Documented/Validated) | 0
Objects with no owner (neither business nor technical) | 0
Objects with no technical owner | 0
Low or Unknown confidence objects | 0
Critical objects not yet Documented/Validated | 0
Dependency rows recorded | 0
Example rows still present (all sheets) | 22 |  |  |  | Fictional; delete when ready
OBJECTS BY TYPE (Object Inventory)
Object Type | Discovered | Documented | % Documented | No Owner
Table | 0 | 0 |  | 0
Field | 0 | 0 |  | 0
Application | 0 | 0 |  | 0
Module | 0 | 0 |  | 0
Flow | 0 | 0 |  | 0
Subflow | 0 | 0 |  | 0
Flow Action | 0 | 0 |  | 0
Business Rule | 0 | 0 |  | 0
Client Script | 0 | 0 |  | 0
UI Policy | 0 | 0 |  | 0
UI Action | 0 | 0 |  | 0
Script Include | 0 | 0 |  | 0
ACL | 0 | 0 |  | 0
Role | 0 | 0 |  | 0
Group | 0 | 0 |  | 0
Catalog Item | 0 | 0 |  | 0
Variable | 0 | 0 |  | 0
Variable Set | 0 | 0 |  | 0
Record Producer | 0 | 0 |  | 0
Notification | 0 | 0 |  | 0
Scheduled Job | 0 | 0 |  | 0
Integration | 0 | 0 |  | 0
REST API | 0 | 0 |  | 0
Data Source | 0 | 0 |  | 0
Transform Map | 0 | 0 |  | 0
Report | 0 | 0 |  | 0
Dashboard | 0 | 0 |  | 0
Widget | 0 | 0 |  | 0
Portal | 0 | 0 |  | 0
Knowledge Base | 0 | 0 |  | 0
Other | 0 | 0 |  | 0

## Architecture Overview
ARCHITECTURE OVERVIEW - the front page of your instance. Fill what you can verify; leave the rest blank and log an Unknown. Do not guess.
Item | Value | Evidence / Source | Confidence | Last Verified | Notes / Linked Unknown ID
INSTANCE
Instance name |  |  | Unknown
Instance URL (production) |  |  | Unknown
Sub-production instance(s) and URLs |  |  | Unknown
Production / sub-production (this record is for) |  |  | Unknown
ServiceNow version / release |  |  | Unknown
Last upgrade (date) |  |  | Unknown
Next planned upgrade (date) |  |  | Unknown
Upgrade owner |  |  | Unknown
PEOPLE
Platform owner |  |  | Unknown
Primary administrator |  |  | Unknown
Backup administrator |  |  | Unknown
Technical owner |  |  | Unknown
Business owner |  |  | Unknown
Vendor / partner support |  |  | Unknown
Now Support authorized contacts |  |  | Unknown
Security contact |  |  | Unknown
WHAT IS ON THE PLATFORM
Major applications (see Applications sheet) |  |  | Unknown
Major modules |  |  | Unknown
Major business processes (see Business Processes sheet) |  |  | Unknown
Major external systems |  |  | Unknown
Major integrations (see Integrations sheet) |  |  | Unknown
Major customizations |  |  | Unknown
Critical platform dependencies (SSO, MID, email, external APIs) |  |  | Unknown
PROCESS & GOVERNANCE
How changes move to production |  |  | Unknown
Change approval process |  |  | Unknown
Existing documentation location |  |  | Unknown
Testing approach (ATF / manual) |  |  | Unknown
Monitoring / alerting in place |  |  | Unknown
Architecture diagram location (Obsidian: 01 - PLATFORM/Diagram Library) |  |  | Unknown
ARCHITECTURE LAYERS (live counts from your sheets; examples excluded)
Layer | Where documented | Rows recorded | Documented / Validated
Applications | Applications | 0 | 0
Data Model (Tables) | Tables | 0 | 0
Service Catalog | Catalog Items | 0 | 0
Automation (Flows) | Flows | 0 | 0
Scripts & Rules | Scripts & Rules | 0 | 0
Integrations | Integrations | 0 | 0
Security | Security | 0 | 0
Business Processes | Business Processes | 0 | 0
Reporting / Portals / UI | Object Inventory (types Report, Dashboard, Widget, Portal) | 0 | 0

## Object Inventory
MASTER OBJECT INVENTORY - one row per important object. Row = 'it exists'. Detail sheets/notes = 'how it works'. Examples are yellow/italic (IDs start EX-) and are excluded from Dashboard counts.
Object ID | Object Name | Display Name | Object Type | Application | Scope | Purpose | Business Process | Business Owner | Technical Owner | Status | Active/Inactive | OOTB/Custom | Criticality | Documentation Status | Confidence | Dependencies | Dependents | Related Objects | Last Reviewed | Access Needed | sys_id / Link | Detail Lives In | Notes
EX-OBJ-001 | u_ex_asset_request | Asset Request | Table | EXAMPLE Asset Requests | x_ex_assetreq | Stores each laptop/asset request | EXAMPLE Laptop Request |  |  | In Use | Active | Custom | Critical | Documented | High | EX Laptop Request Fulfillment (updates) | EX Set Cost Center Default; EX ACL write |  |  | Elevated Application |  | Tables | EXAMPLE - FICTIONAL. Not part of your environment. Delete when you no longer need it.
EX-OBJ-002 | EX Laptop Request | Laptop Request | Catalog Item | EXAMPLE Asset Requests | x_ex_assetreq | Employee-facing request form | EXAMPLE Laptop Request |  |  | In Use | Active | Custom | High | Documented | High | EX Laptop Request Fulfillment | Employees (portal) |  |  | Basic User |  | Catalog Items | EXAMPLE - FICTIONAL. Not part of your environment. Delete when you no longer need it.
EX-OBJ-003 | EX Laptop Request Fulfillment | Laptop Request Fulfillment | Flow | EXAMPLE Asset Requests | x_ex_assetreq | Approval, task creation, record updates | EXAMPLE Laptop Request |  |  | In Use | Active | Custom | Critical | Partially Documented | Medium | EX Get Manager Approval; u_ex_asset_request; EX HR Employee Lookup | EX Laptop Request |  |  | Admin |  | Flows | EXAMPLE - FICTIONAL. Not part of your environment. Delete when you no longer need it.
EX-OBJ-004 | EX Set Cost Center Default | Set Cost Center Default | Business Rule | EXAMPLE Asset Requests | x_ex_assetreq | UNKNOWN - see EX-U-001 | EXAMPLE Laptop Request |  |  | In Use | Active | Custom | Medium | Discovered | Low | EXCostCenterUtil | u_ex_asset_request inserts |  |  | Admin |  | Scripts & Rules | EXAMPLE - FICTIONAL. Not part of your environment. Delete when you no longer need it.
EX-OBJ-005 | EX HR Employee Lookup | HR Employee Lookup | Integration | EXAMPLE Integrations | global | Looks up employee data in a (fictional) HR system | EXAMPLE Laptop Request |  |  | In Use | Active | Custom | High | Partially Documented | Low | External HR system | EX Laptop Request Fulfillment |  |  | Admin |  | Integrations | EXAMPLE - FICTIONAL. Not part of your environment. Delete when you no longer need it.
EX-OBJ-006 | x_ex_assetreq.fulfiller | Asset Fulfiller | Role | EXAMPLE Asset Requests | x_ex_assetreq | Lets fulfillers work asset requests |  |  |  | In Use | Active | Custom | Medium | Documented | Medium |  | EX ACL write u_ex_asset_request |  |  | Admin |  | Security | EXAMPLE - FICTIONAL. Not part of your environment. Delete when you no longer need it.
Note on H2: Which business process breaks if this stops working? Use the Process Name from the Business Processes sheet.
Note on I2: Person accountable for the business outcome. If unknown, leave blank (dashboard counts it) and log an Unknown.
Note on J2: Person accountable for keeping it working technically. Blank is a risk, not an error.
Note on M2: OOTB = untouched out-of-box. Customized OOTB = OOTB object modified (upgrade risk). Custom = built here. Check the record's update/customization indicators and scope.
Note on N2: Critical = a business process stops or there is compliance/safety impact if this fails. High = major degradation. Medium = workaround exists. Low = minor/cosmetic.
Note on O2: Not Started -> Discovered (you know it exists) -> Partially Documented -> Documented (template complete) -> Validated (SME or direct verification) -> Needs Update (platform changed).
Note on P2: High = verified directly in ServiceNow. Medium = strongly supported but not fully verified. Low = inferred, needs validation. Unknown = not looked at yet.
Note on Q2: What this object needs to work. Also add rows on the Dependencies sheet - that sheet drives Impact Check.
Note on R2: What relies on this object. This is the 'what breaks if I change it' list.
Note on T2: Date you last compared this row against the live platform (ServiceNow wins if they disagree).
Note on U2: Lowest access level that lets you VERIFY this item. If you cannot verify it at your current access, leave Confidence at Low/Unknown and use this column as evidence for an access request.

## Applications
APPLICATIONS & MODULES - what is installed/used and why. Start here for Days 4-5 of the plan.
App ID | Application Name | Scope | Source (OOTB / Store / Custom) | Version | Active | Purpose | Business Owner | Technical Owner | Key Modules | Key Tables | Key Business Processes | Primary Users / Groups | Criticality | Documentation Status | Confidence | Evidence / Source | Access Needed | Last Reviewed | Notes
EX-APP-001 | EXAMPLE Asset Requests | x_ex_assetreq | Custom | 1.2 | Active | Employee asset requests |  |  | Request Asset; Fulfill Asset | u_ex_asset_request | EXAMPLE Laptop Request | All employees; EX Asset Fulfillment | High | Partially Documented | Medium |  | Basic User |  | EXAMPLE - FICTIONAL. Not part of your environment. Delete when you no longer need it.
Note on H2: Person accountable for the business outcome. If unknown, leave blank (dashboard counts it) and log an Unknown.
Note on I2: Person accountable for keeping it working technically. Blank is a risk, not an error.
Note on N2: Critical = a business process stops or there is compliance/safety impact if this fails. High = major degradation. Medium = workaround exists. Low = minor/cosmetic.
Note on O2: Not Started -> Discovered (you know it exists) -> Partially Documented -> Documented (template complete) -> Validated (SME or direct verification) -> Needs Update (platform changed).
Note on P2: High = verified directly in ServiceNow. Medium = strongly supported but not fully verified. Low = inferred, needs validation. Unknown = not looked at yet.
Note on Q2: Where you saw it: record URL or sys_id, screenshot, SME name + date, ticket number. If you cannot point to it, it is not High confidence.
Note on R2: Lowest access level that lets you VERIFY this item. If you cannot verify it at your current access, leave Confidence at Low/Unknown and use this column as evidence for an access request.
Note on S2: Date you last compared this row against the live platform (ServiceNow wins if they disagree).

## Tables
TABLES / DATA MODEL - one row per table. Tip: for each table, ask 'who writes it, who reads it, what fires when a row changes, who can see it?'
Table ID | Table Name | Label | Application | Scope | Extends (Parent Table) | Child Tables | Purpose | Business Process | Business Owner | Technical Owner | Primary Key | Display Field | Record Volume | Retention / Archive | Important Fields | Sensitive Data | Data Source | Tables This References | Tables Referencing This | Many-to-Many Relationships | Dependency Notes | Business Rules | Flows | Client Scripts | UI Policies | Script Includes | Scheduled Processes | Other Automation | Read ACLs | Create ACLs | Write ACLs | Delete ACLs | Roles | Groups | Sensitive-Data Restrictions | Written To By (systems) | Read By (systems) | APIs | Import Sets | Transform Maps | MID Server Dependencies | OOTB/Custom | Customized OOTB Objects | Reason for Customization | Upgrade Implications | Technical Debt | Criticality | Unknowns (link IDs) | Open Questions | Documentation Status | Confidence | Evidence / Source | Access Needed | Last Reviewed | Notes
EX-TBL-001 | u_ex_asset_request | Asset Request | EXAMPLE Asset Requests | x_ex_assetreq | task |  | One row per asset request | EXAMPLE Laptop Request |  |  | sys_id | number | ~400/month (fictional) |  | u_cost_center; u_asset_type; state | None identified | Catalog + flow | sys_user; cmn_cost_center |  |  |  | EX Set Cost Center Default | EX Laptop Request Fulfillment | [7 empty] | EX ACL write u_ex_asset_request |  | x_ex_assetreq.fulfiller | [8 empty] | Custom |  |  |  |  | Critical | EX-U-001 |  | Documented | High | Fictional | Admin |  | EXAMPLE - FICTIONAL. Not part of your environment. Delete when you no longer need it.
Note on I2: Which business process breaks if this stops working? Use the Process Name from the Business Processes sheet.
Note on J2: Person accountable for the business outcome. If unknown, leave blank (dashboard counts it) and log an Unknown.
Note on K2: Person accountable for keeping it working technically. Blank is a risk, not an error.
Note on AQ2: OOTB = untouched out-of-box. Customized OOTB = OOTB object modified (upgrade risk). Custom = built here. Check the record's update/customization indicators and scope.
Note on AV2: Critical = a business process stops or there is compliance/safety impact if this fails. High = major degradation. Medium = workaround exists. Low = minor/cosmetic.
Note on AY2: Not Started -> Discovered (you know it exists) -> Partially Documented -> Documented (template complete) -> Validated (SME or direct verification) -> Needs Update (platform changed).
Note on AZ2: High = verified directly in ServiceNow. Medium = strongly supported but not fully verified. Low = inferred, needs validation. Unknown = not looked at yet.
Note on BA2: Where you saw it: record URL or sys_id, screenshot, SME name + date, ticket number. If you cannot point to it, it is not High confidence.
Note on BB2: Lowest access level that lets you VERIFY this item. If you cannot verify it at your current access, leave Confidence at Low/Unknown and use this column as evidence for an access request.
Note on BC2: Date you last compared this row against the live platform (ServiceNow wins if they disagree).

## Fields
FIELDS - document only fields that matter: referenced by automation, ACLs, reports, integrations, or that you had to ask about. Column T is the point: what happens downstream when this value changes?
Field ID | Table | Field Name (element) | Label | Type | Length | Reference Table | Reference Qualifier | Default Value | Mandatory | Read-only | Choice Field | Choices | Calculated | Attributes | Dictionary Overrides | Business Purpose | Read By (rules/flows/reports) | Written By (rules/flows/integrations) | Downstream Behavior (what changes when the value changes) | Dependencies | Criticality | Documentation Status | Confidence | Evidence / Source | Access Needed | Last Reviewed | Notes
EX-FLD-001 | u_ex_asset_request | u_cost_center | Cost Center | Reference |  | cmn_cost_center | active=true |  | Yes | [6 empty] | Charges the asset to a department | Fulfillment flow; Finance report | EX Set Cost Center Default; requester | Selects approver group in flow; changes Finance report grouping |  | High | Documented | Medium |  | Admin |  | EXAMPLE - FICTIONAL. Not part of your environment. Delete when you no longer need it.
Note on U2: What this object needs to work. Also add rows on the Dependencies sheet - that sheet drives Impact Check.
Note on V2: Critical = a business process stops or there is compliance/safety impact if this fails. High = major degradation. Medium = workaround exists. Low = minor/cosmetic.
Note on W2: Not Started -> Discovered (you know it exists) -> Partially Documented -> Documented (template complete) -> Validated (SME or direct verification) -> Needs Update (platform changed).
Note on X2: High = verified directly in ServiceNow. Medium = strongly supported but not fully verified. Low = inferred, needs validation. Unknown = not looked at yet.
Note on Y2: Where you saw it: record URL or sys_id, screenshot, SME name + date, ticket number. If you cannot point to it, it is not High confidence.
Note on Z2: Lowest access level that lets you VERIFY this item. If you cannot verify it at your current access, leave Confidence at Low/Unknown and use this column as evidence for an access request.
Note on AA2: Date you last compared this row against the live platform (ServiceNow wins if they disagree).

## Catalog Items
SERVICE CATALOG ITEMS - trace one item end-to-end: what the requester sees -> what records/approvals/tasks/notifications it creates.
Catalog Item ID | Catalog | Category | Name | Technical Name | Business Owner | Technical Owner | Purpose | Business Process | Active | Criticality | Available To (user criteria / roles) | Variables | Variable Sets | UI Policies | Catalog Client Scripts | Reference Qualifiers | Flow | Subflows | Approvals | Tasks | Notifications | Tables Touched | Integrations | Users / Groups (requesters, fulfillers) | Dependencies | Known Issues | Documentation Status | Confidence | Evidence / Source | Access Needed | Last Reviewed | Notes
EX-CI-001 | Employee Services | Hardware | EXAMPLE Laptop Request | ex_laptop_request |  |  | Request a laptop | EXAMPLE Laptop Request | Active | High | All employees | laptop_model; cost_center; justification |  |  |  |  | EX Laptop Request Fulfillment | EX Get Manager Approval | Manager | Fulfillment task -> EX Asset Fulfillment | Approval request; Shipped | sc_request; sc_req_item; u_ex_asset_request | EX HR Employee Lookup |  |  |  | Partially Documented | Medium |  | Basic User |  | EXAMPLE - FICTIONAL. Not part of your environment. Delete when you no longer need it.
Note on F2: Person accountable for the business outcome. If unknown, leave blank (dashboard counts it) and log an Unknown.
Note on G2: Person accountable for keeping it working technically. Blank is a risk, not an error.
Note on I2: Which business process breaks if this stops working? Use the Process Name from the Business Processes sheet.
Note on K2: Critical = a business process stops or there is compliance/safety impact if this fails. High = major degradation. Medium = workaround exists. Low = minor/cosmetic.
Note on Z2: What this object needs to work. Also add rows on the Dependencies sheet - that sheet drives Impact Check.
Note on AB2: Not Started -> Discovered (you know it exists) -> Partially Documented -> Documented (template complete) -> Validated (SME or direct verification) -> Needs Update (platform changed).
Note on AC2: High = verified directly in ServiceNow. Medium = strongly supported but not fully verified. Low = inferred, needs validation. Unknown = not looked at yet.
Note on AD2: Where you saw it: record URL or sys_id, screenshot, SME name + date, ticket number. If you cannot point to it, it is not High confidence.
Note on AE2: Lowest access level that lets you VERIFY this item. If you cannot verify it at your current access, leave Confidence at Low/Unknown and use this column as evidence for an access request.
Note on AF2: Date you last compared this row against the live platform (ServiceNow wins if they disagree).

## Variables
VARIABLES - one row per variable that drives behavior (approvals, routing, integrations). Skip purely cosmetic ones.
Variable ID | Variable Name | Label | Type | Catalog Item | Variable Set | Reference Table | Reference Qualifier | Default | Mandatory | Read-only | Visibility Conditions | Catalog Client Scripts | UI Policies | Feeds Into (flow/script/task field that reads it) | Dependencies | Criticality | Documentation Status | Confidence | Evidence / Source | Access Needed | Last Reviewed | Notes
EX-VAR-001 | laptop_model | Laptop Model | Select Box | EXAMPLE Laptop Request |  |  |  |  | Yes |  |  |  |  | Flow branches on model to pick approver; sets u_asset_type |  | High | Documented | Medium |  | Basic User |  | EXAMPLE - FICTIONAL. Not part of your environment. Delete when you no longer need it.
Note on P2: What this object needs to work. Also add rows on the Dependencies sheet - that sheet drives Impact Check.
Note on Q2: Critical = a business process stops or there is compliance/safety impact if this fails. High = major degradation. Medium = workaround exists. Low = minor/cosmetic.
Note on R2: Not Started -> Discovered (you know it exists) -> Partially Documented -> Documented (template complete) -> Validated (SME or direct verification) -> Needs Update (platform changed).
Note on S2: High = verified directly in ServiceNow. Medium = strongly supported but not fully verified. Low = inferred, needs validation. Unknown = not looked at yet.
Note on T2: Where you saw it: record URL or sys_id, screenshot, SME name + date, ticket number. If you cannot point to it, it is not High confidence.
Note on U2: Lowest access level that lets you VERIFY this item. If you cannot verify it at your current access, leave Confidence at Low/Unknown and use this column as evidence for an access request.
Note on V2: Date you last compared this row against the live platform (ServiceNow wins if they disagree).

## Flows
FLOWS / AUTOMATION - the 2 questions: (1) if this flow stops, what breaks? (col AE) (2) if I change table/field X, which flows are affected? (filter 'Tables Read/Updated').
Flow ID | Flow Name | Technical Name | Component Type | Application | Scope | Active | Business Owner | Technical Owner | Purpose | Business Process | Trigger | Trigger Conditions | Inputs | Outputs | Tables Read | Tables Created | Tables Updated | Subflows Called | Actions Used | Script Actions | Integrations | Notifications | Approvals | Error Handling | Failure Behavior | Logging | Retry Behavior | Dependencies | Dependents | If This Stops, What Business Process Breaks? | Criticality | Known Issues | Technical Debt | Documentation Status | Confidence | Evidence / Source | Access Needed | Last Reviewed | Notes
EX-FLOW-001 | EX Laptop Request Fulfillment | x_ex_assetreq.laptop_fulfillment | Flow | EXAMPLE Asset Requests | x_ex_assetreq | Active |  |  | Orchestrates approval, task, and record updates | EXAMPLE Laptop Request | Service Catalog (request item created) | Catalog item = EX Laptop Request |  |  | sc_req_item; sys_user | u_ex_asset_request; sc_task | u_ex_asset_request; sc_req_item | EX Get Manager Approval |  |  | EX HR Employee Lookup |  | Manager | None observed (example) | UNKNOWN | Flow execution only | None |  |  | No laptop requests get approved or fulfilled; requests sit in 'Open' | Critical | No alerting on failed executions (example) |  | Partially Documented | Medium |  | Admin |  | EXAMPLE - FICTIONAL. Not part of your environment. Delete when you no longer need it.
Note on H2: Person accountable for the business outcome. If unknown, leave blank (dashboard counts it) and log an Unknown.
Note on I2: Person accountable for keeping it working technically. Blank is a risk, not an error.
Note on K2: Which business process breaks if this stops working? Use the Process Name from the Business Processes sheet.
Note on AC2: What this object needs to work. Also add rows on the Dependencies sheet - that sheet drives Impact Check.
Note on AD2: What relies on this object. This is the 'what breaks if I change it' list.
Note on AF2: Critical = a business process stops or there is compliance/safety impact if this fails. High = major degradation. Medium = workaround exists. Low = minor/cosmetic.
Note on AI2: Not Started -> Discovered (you know it exists) -> Partially Documented -> Documented (template complete) -> Validated (SME or direct verification) -> Needs Update (platform changed).
Note on AJ2: High = verified directly in ServiceNow. Medium = strongly supported but not fully verified. Low = inferred, needs validation. Unknown = not looked at yet.
Note on AK2: Where you saw it: record URL or sys_id, screenshot, SME name + date, ticket number. If you cannot point to it, it is not High confidence.
Note on AL2: Lowest access level that lets you VERIFY this item. If you cannot verify it at your current access, leave Confidence at Low/Unknown and use this column as evidence for an access request.
Note on AM2: Date you last compared this row against the live platform (ServiceNow wins if they disagree).

## Scripts & Rules
SCRIPTS & RULES - Business Rules, Client Scripts, Script Includes, UI Actions, etc. Hunt for hidden dependencies: hard-coded sys_ids, group/user names, other tables written, calls to other scripts (col S).
Script ID | Name | Script Type | Technical Name | Application | Scope | Table | Active | Trigger / When It Runs | Order | Conditions | Purpose (verified, or write UNKNOWN) | Reads | Writes | Functions / Script Includes Called | Called By | Tables Affected | Other Dependencies | Hard-coded Values (sys_ids, names, emails, URLs) | Potential Side Effects | Performance Concerns | Security Concerns | Criticality | OOTB/Custom | Known Issues | Technical Debt | Documentation Status | Confidence | Evidence / Source | Access Needed | Last Reviewed | Notes
EX-SCR-001 | EX Set Cost Center Default | Business Rule |  | EXAMPLE Asset Requests | x_ex_assetreq | u_ex_asset_request | Active | Before insert | 100 | cost center is empty | UNKNOWN - appears to default cost center; reason not verified | sys_user.department | u_ex_asset_request.u_cost_center | EXCostCenterUtil.getDefault() |  | u_ex_asset_request |  | One hard-coded group sys_id in line 14 (example) | Overrides requester choice if department blank |  |  | Medium | Custom |  | Hard-coded sys_id | Discovered | Low |  | Admin |  | EXAMPLE - FICTIONAL. Not part of your environment. Delete when you no longer need it.
Note on W2: Critical = a business process stops or there is compliance/safety impact if this fails. High = major degradation. Medium = workaround exists. Low = minor/cosmetic.
Note on X2: OOTB = untouched out-of-box. Customized OOTB = OOTB object modified (upgrade risk). Custom = built here. Check the record's update/customization indicators and scope.
Note on AA2: Not Started -> Discovered (you know it exists) -> Partially Documented -> Documented (template complete) -> Validated (SME or direct verification) -> Needs Update (platform changed).
Note on AB2: High = verified directly in ServiceNow. Medium = strongly supported but not fully verified. Low = inferred, needs validation. Unknown = not looked at yet.
Note on AC2: Where you saw it: record URL or sys_id, screenshot, SME name + date, ticket number. If you cannot point to it, it is not High confidence.
Note on AD2: Lowest access level that lets you VERIFY this item. If you cannot verify it at your current access, leave Confidence at Low/Unknown and use this column as evidence for an access request.
Note on AE2: Date you last compared this row against the live platform (ServiceNow wins if they disagree).

## Integrations
INTEGRATIONS - every connection in or out. An integration with no known owner, credential expiry or alerting is a risk row waiting to be written.
Integration ID | Integration Name | External System | Direction | Purpose | Technology | API / Service Used | Endpoint / Connection | Authentication | Integration User | Credential Owner / Expiry | MID Server | Data Source | Import Set | Transform Map | Target Table | Schedule | Trigger | Data Exchanged | Failure Logging | Alerting | Retry / Recovery | Dependencies | Business Owner | Technical Owner | External Contact | Active | Criticality | Known Issues | Documentation Status | Confidence | Evidence / Source | Access Needed | Last Reviewed | Notes
EX-INT-001 | EX HR Employee Lookup | EXAMPLE HR System (fictional) | Outbound | Fetch employee manager/cost center | REST |  | https://hr.example.invalid/api (fictional) | OAuth 2.0 | UNKNOWN | UNKNOWN | [6 empty] | Called from fulfillment flow | employee id -> manager, cost center | Unknown | None known | [5 empty] | Active | High |  | Partially Documented | Low |  | Admin |  | EXAMPLE - FICTIONAL. Not part of your environment. Delete when you no longer need it.
Note on W2: What this object needs to work. Also add rows on the Dependencies sheet - that sheet drives Impact Check.
Note on X2: Person accountable for the business outcome. If unknown, leave blank (dashboard counts it) and log an Unknown.
Note on Y2: Person accountable for keeping it working technically. Blank is a risk, not an error.
Note on AB2: Critical = a business process stops or there is compliance/safety impact if this fails. High = major degradation. Medium = workaround exists. Low = minor/cosmetic.
Note on AD2: Not Started -> Discovered (you know it exists) -> Partially Documented -> Documented (template complete) -> Validated (SME or direct verification) -> Needs Update (platform changed).
Note on AE2: High = verified directly in ServiceNow. Medium = strongly supported but not fully verified. Low = inferred, needs validation. Unknown = not looked at yet.
Note on AF2: Where you saw it: record URL or sys_id, screenshot, SME name + date, ticket number. If you cannot point to it, it is not High confidence.
Note on AG2: Lowest access level that lets you VERIFY this item. If you cannot verify it at your current access, leave Confidence at Low/Unknown and use this column as evidence for an access request.
Note on AH2: Date you last compared this row against the live platform (ServiceNow wins if they disagree).

## Security
SECURITY - roles, groups and ACLs in one table (filter by Record Type). Answers: who can SEE it, CHANGE it, EXECUTE it, and what happens if a role/group/ACL changes?
Security ID | Record Type | Name (role / group / ACL name) | Purpose | Table (ACL) | Field (ACL) | Operation (ACL) | ACL Condition | ACL Script | Required Roles / Parent Roles / Group Roles | Assigned Users / Members (counts or names) | Assigned Groups | Apps / Modules Affected | Privileges / Effect (who can see/change/execute) | Manager / Owner | Business Function | Responsibilities | Dependencies | What Happens If This Changes? | Security Risk | Active | Criticality | Documentation Status | Confidence | Evidence / Source | Access Needed | Last Reviewed | Notes
EX-SEC-001 | Role | x_ex_assetreq.fulfiller | Work asset requests | [5 empty] | Contains: (none) |  | EX Asset Fulfillment | EXAMPLE Asset Requests | Read/write u_ex_asset_request |  |  |  |  | Fulfillers lose access to request records |  |  | Medium | Documented | Medium |  | Admin |  | EXAMPLE - FICTIONAL. Not part of your environment. Delete when you no longer need it.
EX-SEC-002 | ACL | EX ACL write u_ex_asset_request |  | u_ex_asset_request | * | write |  |  | x_ex_assetreq.fulfiller |  |  |  | Only fulfillers can edit |  |  |  |  | Widening it lets requesters edit approved requests |  |  | High | Documented | Medium |  | Admin |  | EXAMPLE - FICTIONAL. Not part of your environment. Delete when you no longer need it.
Note on R2: What this object needs to work. Also add rows on the Dependencies sheet - that sheet drives Impact Check.
Note on V2: Critical = a business process stops or there is compliance/safety impact if this fails. High = major degradation. Medium = workaround exists. Low = minor/cosmetic.
Note on W2: Not Started -> Discovered (you know it exists) -> Partially Documented -> Documented (template complete) -> Validated (SME or direct verification) -> Needs Update (platform changed).
Note on X2: High = verified directly in ServiceNow. Medium = strongly supported but not fully verified. Low = inferred, needs validation. Unknown = not looked at yet.
Note on Y2: Where you saw it: record URL or sys_id, screenshot, SME name + date, ticket number. If you cannot point to it, it is not High confidence.
Note on Z2: Lowest access level that lets you VERIFY this item. If you cannot verify it at your current access, leave Confidence at Low/Unknown and use this column as evidence for an access request.
Note on AA2: Date you last compared this row against the live platform (ServiceNow wins if they disagree).

## Business Processes
BUSINESS PROCESSES - the spine of this system. Pick 3-5, trace each end-to-end, then link every object you meet back to its process.
Process ID | Process Name | Business Purpose | Process Owner | Trigger | Users Involved | Process Steps (numbered) | ServiceNow Application(s) | Tables | Key Fields | Catalog Items | Flows | Scripts | Notifications | Approvals | Integrations | Reports | Roles / Groups | Manual Steps | Failure Points | Workarounds | Known Pain Points | Business Impact If It Fails | Volume / Frequency | Criticality | Priority to Trace | SME Validated By | SME Validated Date | Documentation Status | Confidence | Evidence / Source | Access Needed | Last Reviewed | Notes
EX-BP-001 | EXAMPLE Laptop Request | Employees get approved equipment quickly | (example) IT Operations Manager | Employee submits catalog item | Employee; Manager; Fulfiller | 1 Employee submits. 2 Manager approves. 3 Fulfillment task created. 4 Fulfiller ships. 5 Asset record updated. | EXAMPLE Asset Requests | sc_req_item; u_ex_asset_request |  | EX Laptop Request | EX Laptop Request Fulfillment | EX Set Cost Center Default |  | Manager | EX HR Employee Lookup |  |  | Shipping handled outside ServiceNow | HR lookup fails -> flow stalls (no alert) |  |  | New hires without equipment |  | High | High |  |  | Partially Documented | Medium |  | Basic User |  | EXAMPLE - FICTIONAL. Not part of your environment. Delete when you no longer need it.
Note on Y2: Critical = a business process stops or there is compliance/safety impact if this fails. High = major degradation. Medium = workaround exists. Low = minor/cosmetic.
Note on AC2: Not Started -> Discovered (you know it exists) -> Partially Documented -> Documented (template complete) -> Validated (SME or direct verification) -> Needs Update (platform changed).
Note on AD2: High = verified directly in ServiceNow. Medium = strongly supported but not fully verified. Low = inferred, needs validation. Unknown = not looked at yet.
Note on AE2: Where you saw it: record URL or sys_id, screenshot, SME name + date, ticket number. If you cannot point to it, it is not High confidence.
Note on AF2: Lowest access level that lets you VERIFY this item. If you cannot verify it at your current access, leave Confidence at Low/Unknown and use this column as evidence for an access request.
Note on AG2: Date you last compared this row against the live platform (ServiceNow wins if they disagree).

## Dependencies
DEPENDENCIES - one row = 'Source --relationship--> Target'. Use the SAME names as Object Inventory so Impact Check can find them. Add the reverse reading for free: anything pointing AT an object is a dependent.
Dependency ID | Source Object ID | Source Type | Source Name | Relationship | Target Object ID | Target Type | Target Name | Dependency Type | Criticality | Evidence | Confidence | Date Recorded | Last Verified | Notes | Helper: Inbound # (do not edit) | Helper: Outbound # (do not edit)
EX-DEP-001 |  | Catalog Item | EX Laptop Request | launches |  | Flow | EX Laptop Request Fulfillment | Automation | High | Fictional | Medium |  |  | EXAMPLE - FICTIONAL. Not part of your environment. Delete when you no longer need it.
EX-DEP-002 |  | Flow | EX Laptop Request Fulfillment | calls |  | Subflow | EX Get Manager Approval | Automation | High | Fictional | Medium |  |  | EXAMPLE - FICTIONAL. Not part of your environment. Delete when you no longer need it.
EX-DEP-003 |  | Flow | EX Laptop Request Fulfillment | updates |  | Table | u_ex_asset_request | Data | Critical | Fictional | Medium |  |  | EXAMPLE - FICTIONAL. Not part of your environment. Delete when you no longer need it. | 1
EX-DEP-004 |  | Flow | EX Laptop Request Fulfillment | calls |  | Integration | EX HR Employee Lookup | Integration | High | Fictional | Low |  |  | EXAMPLE - FICTIONAL. Not part of your environment. Delete when you no longer need it.
EX-DEP-005 |  | Business Rule | EX Set Cost Center Default | runs on |  | Table | u_ex_asset_request | Code | Medium | Fictional | Medium |  |  | EXAMPLE - FICTIONAL. Not part of your environment. Delete when you no longer need it. | 2
EX-DEP-006 |  | Business Rule | EX Set Cost Center Default | calls |  | Script Include | EXCostCenterUtil | Code | Medium | Fictional | Medium |  |  | EXAMPLE - FICTIONAL. Not part of your environment. Delete when you no longer need it.
EX-DEP-007 |  | ACL | EX ACL write u_ex_asset_request | protects |  | Table | u_ex_asset_request | Security | High | Fictional | Medium |  |  | EXAMPLE - FICTIONAL. Not part of your environment. Delete when you no longer need it. | 3
EX-DEP-008 |  | ACL | EX ACL write u_ex_asset_request | requires role |  | Role | x_ex_assetreq.fulfiller | Security | High | Fictional | Medium |  |  | EXAMPLE - FICTIONAL. Not part of your environment. Delete when you no longer need it.
EX-DEP-009 |  | Report | EX Asset Requests Report | reports on |  | Table | u_ex_asset_request | Reporting | Low | Fictional | Low |  |  | EXAMPLE - FICTIONAL. Not part of your environment. Delete when you no longer need it. | 4
Note on J2: Critical = a business process stops or there is compliance/safety impact if this fails. High = major degradation. Medium = workaround exists. Low = minor/cosmetic.
Note on L2: High = verified directly in ServiceNow. Medium = strongly supported but not fully verified. Low = inferred, needs validation. Unknown = not looked at yet.

## Impact Check
IMPACT CHECK - 'If I change this, what could break?'
Object name (exact match to Dependencies sheet): | u_ex_asset_request | <- type an object name (example value is fictional). Then repeat for each dependent you find: that is your second-hop impact.
Rows that point AT this object (dependents): | 4
Rows this object points TO (it relies on): | 0
Confidence warning: | Some links are Low confidence - verify before relying on this list.
IF I CHANGE THIS, THESE COULD BREAK (dependents)
# | Dependent (source object) | Relationship | Other Object Type | Dependency Type | Criticality | Confidence | Evidence
1 | EX Laptop Request Fulfillment | updates | Flow | Data | Critical | Medium | Fictional
2 | EX Set Cost Center Default | runs on | Business Rule | Code | Medium | Medium | Fictional
3 | EX ACL write u_ex_asset_request | protects | ACL | Security | High | Medium | Fictional
4 | EX Asset Requests Report | reports on | Report | Reporting | Low | Low | Fictional
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
THIS OBJECT RELIES ON (its dependencies)
# | Depends On (target object) | Relationship | Other Object Type | Dependency Type | Criticality | Confidence | Evidence
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
Shows first 25 matches per list. If B5 or B6 > 25, filter the Dependencies sheet directly.

## Risks
RISK / TECHNICAL DEBT REGISTER - Overall Risk is automatic: Likelihood (1-3) x Severity (1-4): >=9 Critical, 6-8 High, 3-5 Medium, 1-2 Low. Rows marked 'Suspected' are prompts to verify, not findings.
Risk ID | Date Discovered | Component | Risk Description | Business Impact | Technical Impact | Likelihood | Severity | Overall Risk (auto) | Owner | Recommended Action | Status | Target Date | Mitigation | Evidence | Related Object ID | Access Needed to Verify | Notes
R-001 |  | Platform / staffing | Sole administrator dependency has materialized: previous administrator left | No known owner for platform changes or break-fix | Undocumented configuration; unknown customizations | High | High | Critical |  | Establish platform owner, backup admin, escalation path (see Transition Checklist) | Open |  |  | Stated by workbook owner at project start |  |  | Real entry - not an example. Add date.
R-002 |  | Access | Current access is limited; may be asked to fix issues without access to inspect or change configuration | Delayed resolution; accountability without authority |  | High | Medium | High |  | Use Access Roadmap to request access tied to specific responsibilities | Open |  |  | Stated by workbook owner |  |  | Real entry - not an example.
R-003 |  | Unknown customizations | HYPOTHESIS TO CHECK: Customized OOTB or custom objects exist with no documented purpose | [7 empty] | Suspected | [5 empty] | Assumption: common in inherited instances. Not evidence about YOUR instance. Verify, then set Likelihood/Severity and Status=Open, or Close.
R-004 |  | No documented integrations | HYPOTHESIS TO CHECK: Inbound/outbound connections exist that nobody has inventoried | [7 empty] | Suspected | [5 empty] | Assumption: common in inherited instances. Not evidence about YOUR instance. Verify, then set Likelihood/Severity and Status=Open, or Close.
R-005 |  | Hard-coded logic | HYPOTHESIS TO CHECK: Scripts or flows contain sys_ids, user/group names, emails, or URLs | [7 empty] | Suspected | [5 empty] | Assumption: common in inherited instances. Not evidence about YOUR instance. Verify, then set Likelihood/Severity and Status=Open, or Close.
R-006 |  | Scripts with unclear purpose | HYPOTHESIS TO CHECK: Business rules/script includes nobody can explain | [7 empty] | Suspected | [5 empty] | Assumption: common in inherited instances. Not evidence about YOUR instance. Verify, then set Likelihood/Severity and Status=Open, or Close.
R-007 |  | Inactive former-employee accounts | HYPOTHESIS TO CHECK: Departed staff still own records, integrations, jobs, or hold roles | [7 empty] | Suspected | [5 empty] | Assumption: common in inherited instances. Not evidence about YOUR instance. Verify, then set Likelihood/Severity and Status=Open, or Close.
R-008 |  | Excessive permissions | HYPOTHESIS TO CHECK: Too many users/groups hold admin or powerful roles | [7 empty] | Suspected | [5 empty] | Assumption: common in inherited instances. Not evidence about YOUR instance. Verify, then set Likelihood/Severity and Status=Open, or Close.
R-009 |  | Critical workflows with no monitoring | HYPOTHESIS TO CHECK: Flow or integration failures would go unnoticed | [7 empty] | Suspected | [5 empty] | Assumption: common in inherited instances. Not evidence about YOUR instance. Verify, then set Likelihood/Severity and Status=Open, or Close.
R-010 |  | No error handling | HYPOTHESIS TO CHECK: Flows/scripts fail silently or leave records in limbo | [7 empty] | Suspected | [5 empty] | Assumption: common in inherited instances. Not evidence about YOUR instance. Verify, then set Likelihood/Severity and Status=Open, or Close.
R-011 |  | Manual workarounds | HYPOTHESIS TO CHECK: People compensate for broken or missing automation | [7 empty] | Suspected | [5 empty] | Assumption: common in inherited instances. Not evidence about YOUR instance. Verify, then set Likelihood/Severity and Status=Open, or Close.
R-012 |  | Customized OOTB functionality | HYPOTHESIS TO CHECK: Upgrade will collide with changes to OOTB objects | [7 empty] | Suspected | [5 empty] | Assumption: common in inherited instances. Not evidence about YOUR instance. Verify, then set Likelihood/Severity and Status=Open, or Close.
R-013 |  | No test coverage | HYPOTHESIS TO CHECK: No ATF or documented regression tests for critical processes | [7 empty] | Suspected | [5 empty] | Assumption: common in inherited instances. Not evidence about YOUR instance. Verify, then set Likelihood/Severity and Status=Open, or Close.
R-014 |  | No change documentation | HYPOTHESIS TO CHECK: No record of who changed what and why | [7 empty] | Suspected | [5 empty] | Assumption: common in inherited instances. Not evidence about YOUR instance. Verify, then set Likelihood/Severity and Status=Open, or Close.
R-015 |  | Unknown ownership | HYPOTHESIS TO CHECK: Important objects have no business or technical owner | [7 empty] | Suspected | [5 empty] | Assumption: common in inherited instances. Not evidence about YOUR instance. Verify, then set Likelihood/Severity and Status=Open, or Close.
R-016 |  | Upgrade risks | HYPOTHESIS TO CHECK: Behind on upgrades, skipped upgrades, or unsupported customizations | [7 empty] | Suspected | [5 empty] | Assumption: common in inherited instances. Not evidence about YOUR instance. Verify, then set Likelihood/Severity and Status=Open, or Close.
R-017 |  | Unsupported customizations | HYPOTHESIS TO CHECK: Direct changes to platform internals or unsupported approaches | [7 empty] | Suspected | [5 empty] | Assumption: common in inherited instances. Not evidence about YOUR instance. Verify, then set Likelihood/Severity and Status=Open, or Close.
R-018 |  | Expiring credentials/certificates | HYPOTHESIS TO CHECK: Integration credentials or certificates owned by departed staff | [7 empty] | Suspected | [5 empty] | Assumption: common in inherited instances. Not evidence about YOUR instance. Verify, then set Likelihood/Severity and Status=Open, or Close.
EX-R-001 |  | EX Set Cost Center Default | Business rule has hard-coded group sys_id | Wrong approver if group is replaced |  | Medium | High | High |  | Replace with property/lookup | Open |  |  | Fictional | EX-SCR-001 |  | EXAMPLE - FICTIONAL. Not part of your environment. Delete when you no longer need it.

## Unknowns
UNKNOWNS - the antidote to guessing. Write the question, never a made-up answer. Seeded rows are real questions that apply to almost any inherited instance; answer them for YOUR instance.
Unknown ID | Question | Related Object / ID | Why It Matters | Investigation Method | Access Needed | Who To Ask (SME) | Owner | Priority | Status | Answer | Evidence / Source | Date Raised | Date Resolved | Confidence
U-001 | Who is the platform owner and who is the business owner for ServiceNow overall? |  | Decisions and escalations have no home | Ask manager/CIO office; check ServiceNow contract/Now Support contacts | Basic User |  |  | Critical | Open |  |  |  |  | Unknown
U-002 | Who are the current administrators (including vendor/partner support)? |  | Defines who can actually make and deploy changes | User admin list (needs access) or ask security/IT | Admin |  |  | Critical | Open |  |  |  |  | Unknown
U-003 | Which instances exist (prod, test, dev) and which one is development done in? |  | Changes in the wrong place can hit production | Ask; check instance URLs; look for clone dates in sub-prod | Basic User |  |  | Critical | Open |  |  |  |  | Unknown
U-004 | How are changes moved to production today (update sets, pipeline, direct edits)? |  | Defines change risk and who needs deploy rights | Ask SMEs; later review update sets/versions | Admin |  |  | High | Open |  |  |  |  | Unknown
U-005 | What is the ServiceNow version and when was the last/next upgrade? |  | Upgrade risk and customization compatibility | Instance info page / ask platform owner / Now Support | Basic User |  |  | High | Open |  |  |  |  | Unknown
U-006 | What integrations exist, who owns each external system, and who holds the credentials? |  | Silent breakage when credentials/certs expire | Ask app owners; review REST messages, import sets, MID, scheduled jobs (needs access) | Admin |  |  | Critical | Open |  |  |  |  | Unknown
U-007 | Which scheduled jobs run, and what business process depends on each? |  | Failed jobs may stop processes without warning | Review scheduled jobs list; correlate with owners | Admin |  |  | High | Open |  |  |  |  | Unknown
U-008 | Is there existing documentation, update-set history, or a handoff note from the former administrator? |  | Fastest source of 'why' | Search shared drives, email, tickets, wiki; ask HR/manager for handoff material | Basic User |  |  | High | Open |  |  |  |  | Unknown
U-009 | Which user accounts own records, jobs, or integrations and are inactive/departed? |  | Orphaned ownership | Reports on inactive users with assignments (needs access) | Admin |  |  | High | Open |  |  |  |  | Unknown
U-010 | What testing exists for critical processes (ATF, manual scripts)? |  | Determines how safely changes can be made | Ask; review ATF suites if available | Elevated Application |  |  | Medium | Open |  |  |  |  | Unknown
U-011 | What am I formally expected to own, with what authority and access? |  | Avoid ownership without authority | Transition Checklist conversation with manager | Basic User |  |  | Critical | Open |  |  |  |  | Unknown
U-012 | Which 3-5 business processes matter most and who owns each? |  | Focuses discovery on real work | Stakeholder interviews | Basic User |  |  | Critical | Open |  |  |  |  | Unknown
EX-U-001 | EXAMPLE: Why does 'EX Set Cost Center Default' exist? | EX-SCR-001 | Might be required by Finance; removal could break reporting | Check script comments, update set description, ask Finance and former team | Admin |  |  | Medium | Open | (not answered - do not invent) | EXAMPLE - FICTIONAL. Not part of your environment. Delete when you no longer need it. |  |  | Unknown
Note on F2: Lowest access level that lets you VERIFY this item. If you cannot verify it at your current access, leave Confidence at Low/Unknown and use this column as evidence for an access request.
Note on L2: Where you saw it: record URL or sys_id, screenshot, SME name + date, ticket number. If you cannot point to it, it is not High confidence.
Note on O2: High = verified directly in ServiceNow. Medium = strongly supported but not fully verified. Low = inferred, needs validation. Unknown = not looked at yet.

## Decisions
ARCHITECTURE DECISION LOG - record NEW decisions here. If you discover an OLD decision, record it as 'Reconstructed' and keep confidence honest: you are recording what you can prove, not guessing the reason.
Decision ID | Date | Origin | Problem | Context | Options Considered | Decision | Why | Impact | Objects Affected | Risks | Rollback | Approver | Review Date | Status | Confidence | Evidence / Source
EX-D-001 |  | New decision | Approvals duplicated across flows | Three flows each built their own approval steps | A) copy logic B) shared subflow C) leave as is | Use shared subflow 'EX Get Manager Approval' | One place to fix approver logic | Fewer places to maintain | EX Laptop Request Fulfillment; EX Get Manager Approval | Subflow change affects all callers | Restore previous flow versions | (example) Platform Owner |  | Proposed | High | EXAMPLE - FICTIONAL. Not part of your environment. Delete when you no longer need it.
Note on P2: High = verified directly in ServiceNow. Medium = strongly supported but not fully verified. Low = inferred, needs validation. Unknown = not looked at yet.
Note on Q2: Where you saw it: record URL or sys_id, screenshot, SME name + date, ticket number. If you cannot point to it, it is not High confidence.

## Change History
CHANGE HISTORY - changes YOU or your team make from now on. Do not backfill history you cannot prove; use Decisions (Reconstructed) or Unknowns for that.
Change ID | Date | Change | Reason | Requestor | Implementer | Objects Affected | Testing | Approval | Production Date | Result | Rollback | Follow-up | Ticket / Update Set | Notes
EX-C-001 |  | Moved approver lookup into subflow | See EX-D-001 | (example) | (example) | EX Laptop Request Fulfillment | Submitted 3 test requests in sub-prod | (example) Platform Owner |  | Success | Restore flow v3 |  |  | EXAMPLE - FICTIONAL. Not part of your environment. Delete when you no longer need it.

## 30-Day Plan
30-DAY DISCOVERY PLAN - phases not heroics. If a day slips, move on; the goal is a defensible picture, not completeness.
Day | Phase | Focus | What To Do | Output | Workbook Sheet | Typical Access Needed | Status | Date Done | Notes | Days done: | 0 / 30
1 | 1-3 Establish the perimeter | Instances & your access | Record prod and sub-prod URLs. Log in to each. Write down what you CAN open (catalog, lists, reports, knowledge) and what is blocked. Capture your own roles if visible; otherwise ask. | Architecture Overview rows (instance, URL, prod/sub-prod); Unknowns for blanks | Architecture Overview | Basic User | Not Started
2 | 1-3 Establish the perimeter | People & documentation | List: platform owner, admins (incl. vendors), backup, security contact, business owners. Hunt existing docs: shared drives, wiki, email, handoff notes, tickets. Start Transition Checklist conversation with your manager. | Contact list in Architecture Overview; U-001, U-002, U-008 updated; Transition Checklist started | Transition Checklist | Basic User | Not Started
3 | 1-3 Establish the perimeter | Processes, systems, upgrade & dev/test process | List 5-10 candidate business processes and their owners; list external systems you hear about; find out upgrade schedule and how changes reach production. Score candidates (volume, criticality, pain, SME availability). Do NOT try to understand everything. | Business Processes rows (Priority to Trace set); Unknowns for dev/test, upgrades | Business Processes | Basic User | Not Started
4 | 4-7 Platform inventory | Applications & modules | Walk the application navigator. For each app/module: name, scope if visible, who uses it. Add to Applications and Object Inventory. | Applications + Object Inventory rows | Applications | Basic User | Not Started
5 | 4-7 Platform inventory | Catalogs & catalog items | Browse the portal/catalog as a requester. Record catalogs, categories, items, visible variables, who owns each. Note items you cannot see (Access Needed). | Catalog Items rows | Catalog Items | Basic User | Not Started
6 | 4-7 Platform inventory | Tables, roles, groups, reports | From forms/lists you can open, record table names and key fields. Record visible groups/roles, reports and dashboards, knowledge bases. | Tables, Security, Object Inventory rows | Tables | Basic User | Not Started
7 | 4-7 Platform inventory | Flows, scripts, integrations, jobs - and what you could not see | Record anything visible; for everything else create an inventory row with Access Needed set. Draft your first access request from those rows. Review: counts on Dashboard. | Access Roadmap requests drafted; Dashboard snapshot | Dashboard | Elevated Application | Not Started
8 | 8-14 Business process tracing | Choose processes & kickoff | Pick 3-5 processes. Book 30-45 minutes with each process owner: 'Show me how it works. Who does what? What breaks? What workarounds exist?' | Process owners confirmed; interview notes | Business Processes | Basic User | Not Started
9 | 8-14 Business process tracing | Process 1: user side | Trace as the requester (use sub-prod and test records if allowed): catalog item, variables, visibility rules, what the user sees at each step. | Variables rows; process steps draft | Variables | Basic User | Not Started
10 | 8-14 Business process tracing | Process 1: back end | Follow the records: tables, tasks, approvals, notifications, fields changed. Fill Business Processes row, link every object. Record Dependencies as you go. | Tables/Flows/Dependencies rows linked to process | Dependencies | Elevated Application | Not Started
11 | 8-14 Business process tracing | Process 2 | Same trace. Note shared components (same flow, subflow, script include, table) - shared pieces are the highest-impact objects. | Process 2 documented; shared objects flagged | Business Processes | Elevated Application | Not Started
12 | 8-14 Business process tracing | Process 3 | Same trace. | Process 3 documented | Business Processes | Elevated Application | Not Started
13 | 8-14 Business process tracing | Processes 4-5 or shared components | Trace one more process OR deep-dive the shared objects found so far. | More Dependencies; Unknowns logged | Dependencies | Elevated Application | Not Started
14 | 8-14 Business process tracing | Consolidate & first SME validation | Review all Dependencies; run Impact Check on your 5 most shared objects. Validate Process 1 with its owner. Log risks. Send manager a one-page status (Dashboard). | SME validation recorded; first Risks scored | Risks | Basic User | Not Started
15 | 15-21 Deep technical discovery | Flows | For flows in your traced processes: trigger, conditions, tables, subflows, error handling, failure behavior, logging, retries. Answer 'If this stops, what breaks?' | Flows rows | Flows | Admin | Not Started
16 | 15-21 Deep technical discovery | Business rules & script includes | On traced tables: when they run, what they write, what they call, hard-coded values. Unclear purpose = Unknown, never a guess. | Scripts & Rules rows | Scripts & Rules | Admin | Not Started
17 | 15-21 Deep technical discovery | Client-side: client scripts, UI policies, UI actions | Document what changes in the form/portal, and what each can hide, require or set. | Scripts & Rules rows | Scripts & Rules | Admin | Not Started
18 | 15-21 Deep technical discovery | ACLs, roles, groups | For traced tables: who can read/write/create/delete. Look for broad access, inactive owners, powerful roles. | Security rows; security Risks | Security | Security Admin | Not Started
19 | 15-21 Deep technical discovery | Integrations & scheduled jobs | Endpoints, auth, credential owner/expiry, schedules, failure logging, alerting, MID dependencies. | Integrations rows; Risks | Integrations | Admin | Not Started
20 | 15-21 Deep technical discovery | Customizations & upgrade risk | Separate OOTB vs customized OOTB vs custom. Check version, last upgrade, skipped/pending upgrades if visible. Flag upgrade collisions. | OOTB/Custom set; upgrade Risks | Object Inventory | Admin | Not Started
21 | 15-21 Deep technical discovery | Errors, logging, monitoring | Where do failures show up (flow executions, system logs, email logs, import errors)? Who sees them? Note monitoring gaps. Review week. | Monitoring risks; updated Dashboard | Risks | Admin | Not Started
22 | 22-30 Validate & establish ownership | Prioritize unknowns | Sort Unknowns by priority. For each Critical/High: method, person to ask, access needed. Book SME time. | Unknowns triaged | Unknowns | Basic User | Not Started
23 | 22-30 Validate & establish ownership | SME validation: business | Review traced processes with process owners; record validated-by/date; correct the documentation. | Business Processes validated | Business Processes | Basic User | Not Started
24 | 22-30 Validate & establish ownership | SME validation: technical & external | Validate integrations with external owners; confirm customizations with former team/vendor if reachable. | Integrations/Scripts confidence raised | Integrations | Basic User | Not Started
25 | 22-30 Validate & establish ownership | Assign ownership | Propose a business and technical owner for each Critical/High object. Get agreement or log it as an open risk. | Owners filled; 'without owners' count falls | Object Inventory | Basic User | Not Started
26 | 22-30 Validate & establish ownership | Documentation standards & change expectations | Draft naming, review cadence, 'definition of documented', and how changes are requested/tested/approved. Record as Decisions. | Decisions rows | Decisions | Basic User | Not Started
27 | 22-30 Validate & establish ownership | Transition agreement & access request | Complete the Transition Checklist with your manager. Submit access request using the Access Roadmap, tied to responsibilities. | Transition Checklist complete; access request submitted | Transition Checklist | Basic User | Not Started
28 | 22-30 Validate & establish ownership | Risk review | Walk the top 10 risks with your manager/owner; confirm owners and actions. | Risks reviewed | Risks | Basic User | Not Started
29 | 22-30 Validate & establish ownership | 60-90 day improvement backlog | Turn risks, unknowns and tech debt into a prioritized backlog with effort, owner, access required. | Backlog (list on Decisions or your tracker) | Decisions | Basic User | Not Started
30 | 22-30 Validate & establish ownership | Present | Share Dashboard, top risks, traced processes, access request status, proposed ownership model, backlog. | Presentation; agreed next steps | Dashboard | Basic User | Not Started

## Access Matrix
ACCESS MATRIX - what each discovery item usually needs. ASSUMPTION: roles and ACLs vary by instance; treat 'minimum access' as a starting hypothesis and record what ACTUALLY blocked you.
What You Want To Discover | Typical Minimum Access (assumption) | What Limits You | Workaround With Less Access | Set 'Access Needed' To | Verified In My Instance?
Catalog items you can request (names, descriptions, visible variables) | Basic User | Only items available to you via user criteria. Hidden items and technical names are not visible. | Ask owners for item lists; screenshot the form | Basic User
Form field labels, list columns, choice values on tables you can read | Basic User | Labels yes; dictionary details (type/length/reference qualifier) usually need more. | List > Export (if allowed) for visible data | Basic User
Reports, dashboards, knowledge bases shared with you | Basic User | Only shared ones; report definitions may be viewable only to some roles. | Ask report owners for definitions | Basic User
Notifications you receive (sample emails) | Basic User | You see outputs, not conditions or recipients logic. | Keep samples as evidence | Basic User
Approvals/tasks assigned to you; observed process behavior in test | Basic User | Test in sub-prod with permission only. | Ask for test persona accounts | Basic User
Application navigator: apps and modules visible to you | Basic User | Shows only what your roles allow - absence is not proof of non-existence. | Compare with a fulfiller's view | Basic User
Tables, columns, extends relationships (schema) | Elevated Application | Often restricted; some instances allow read of dictionary to analysts. Verify yours. | Ask for dictionary export | Elevated Application
Roles/groups membership lists | Elevated Application | User/group admin visibility varies; may be read-only to some. | Ask for export of role/group reports | Elevated Application
Flow Designer flows, subflows, actions, executions | Elevated Application | Flow Designer roles or admin typically needed to view; executions may be restricted. | Ask flow owner for screenshots/export | Elevated Application
Business rules, client scripts, UI policies, UI actions | Admin | Script records are typically admin-readable; scoped apps may differ. | Request read-only config access | Admin
Script includes and script content | Admin | Same. You need to read code to find hard-coded values. | Read-only developer access in sub-prod | Admin
Scheduled jobs / scheduled flows | Admin | Job list and run history are often admin-only. | Ask for job report | Admin
REST messages, data sources, import sets, transform maps, MID servers | Admin | Integration tables often require integration/admin roles. | Ask integration owner for diagrams | Admin
Credentials/connection records (existence, owner, expiry) | Admin | Secrets are not viewable; existence/metadata may be. | Ask credential owner | Admin
System logs, event log, email log, flow errors, import errors | Admin | Needed for troubleshooting; may be role-limited. | Request log-view access in sub-prod first | Admin
Update sets, customization indicators, version history | Admin | Shows what changed and when; may expose 'why' in descriptions. | Ask for update set export | Admin
Plugins, store apps, versions, upgrade history, instance info | Admin | Some info on instance info page is broader. | Check Now Support / platform owner | Admin
ACL records (view) and ACL changes | Security Admin | Viewing may be admin; editing normally requires an elevated security role. | Request read-only; changes via security team | Security Admin
Impersonation / test as another user | Security Admin | Powerful; treat as audited. Prefer test accounts. | Test accounts per persona | Security Admin
Instance performance, node/DB-level logs, backend queries, clone/restore | Database/Platform | Typically ServiceNow Support/hosting or platform team; not customer-visible. | Open a Now Support case via an authorized contact | Database/Platform
Raw data exports at scale, ETL, direct DB reporting | Database/Platform | Often via approved reporting/data-export mechanisms. | Use approved reports/exports | Database/Platform

## Access Roadmap
ACCESS ROADMAP - capability first, role second. 'Typical access' is an ASSUMPTION: role names differ by instance. Record the real role/ticket in Notes. Ask for access TIED TO A RESPONSIBILITY, not generically.
Level | Capability Needed | Why It Is Needed | Typical ServiceNow Access (verify in your instance) | Risk If Missing | Temporary or Permanent | Request Status | Date Requested | Approver | Date Granted | Notes / Actual Role or Ticket
L1 Discovery | Read/test the processes as a requester and fulfiller (sub-prod) | See behavior without touching config | Standard user + test persona accounts or a fulfiller role in sub-prod | You trace only the happy path; cannot reproduce fulfiller issues | Temporary then review | Not Needed Yet
L1 Discovery | Read-only access to the business tables for traced processes | Know what data exists and who changes it | Table-specific read via role/ACL; or approved exports | Process traces are incomplete; Unknowns pile up | Permanent | Not Needed Yet
L1 Discovery | Ability to export lists/reports you can read | Capture inventory evidence | Export-capable user role on reportable tables | Manual copying; evidence quality drops | Permanent | Not Needed Yet
L2 Application Analyst | Read-only view of configuration (flows, rules, scripts, ACLs, jobs) in sub-prod | Understand how it actually works; find hidden dependencies | Often admin-level; ask for a custom read-only 'configuration viewer' role or sub-prod admin | Cannot answer 'what breaks if I change this' | Permanent (read-only) | Not Needed Yet
L2 Application Analyst | View system logs, email logs, flow executions, import errors | Troubleshoot instead of guess | Admin-level or log-reader roles (varies) | Break-fix is blind; escalations pile up | Permanent (read-only) | Not Needed Yet
L2 Application Analyst | Impersonate/test as users in sub-prod | Reproduce user issues and validate fixes | Impersonation role (audit-sensitive); prefer test accounts | Cannot validate fixes; defects missed | Temporary then review | Not Needed Yet
L2 Application Analyst | Run/review automated tests (ATF) if used | Regression safety | ATF tester/admin roles (if ATF is in use) | No safe way to verify changes | Permanent | Not Needed Yet
L2 Application Analyst | Read update sets / change history | Find the 'why' and timeline | Admin-level; request read-only | Unknown history; more Unknowns | Permanent (read-only) | Not Needed Yet
L3 Application Administrator | Maintain catalog items, variables, UI policies for owned apps | Make approved configuration changes | Catalog admin/editor roles scoped to your catalogs | Requests for simple changes stall | Permanent | Not Needed Yet
L3 Application Administrator | Create/edit flows and application scripts in sub-prod (scope-limited) | Implement approved changes | Flow Designer + scoped developer roles in sub-prod | You carry accountability without ability to deliver | Permanent (sub-prod) | Not Needed Yet
L3 Application Administrator | Manage assignment groups and application role assignment | Keep fulfillment working | Group/user admin delegated to your app scope | Fulfillment stalls waiting on others | Permanent | Not Needed Yet
L3 Application Administrator | Prepare, test, and promote changes via agreed process | Deliver changes safely | Update-set/pipeline permissions; production deploy may stay with platform admin | Unclear who deploys; changes bypass control | Permanent for sub-prod; production per policy | Not Needed Yet
L3 Application Administrator | Manage notifications, reports, dashboards for owned apps | Operational improvements | Report/notification admin roles (scoped) | Business asks go unfulfilled | Permanent | Not Needed Yet
L4 Platform Administrator | Full admin in sub-prod and agreed production admin | Platform-wide troubleshooting and configuration | Admin role (and elevated security role where applicable) | You cannot fix platform-level issues | Permanent only if formally assigned | Not Needed Yet
L4 Platform Administrator | Integration, credentials, MID server management | Own integrations | Admin / integration roles | Integration failures cannot be resolved | Permanent only if formally assigned | Not Needed Yet
L4 Platform Administrator | Plugin/store app management, upgrades, instance clones | Lifecycle management | Admin + Now Support authorized contact | Upgrades depend on others | Permanent only if formally assigned | Not Needed Yet
L4 Platform Administrator | ACL/security configuration | Security accountability | Elevated security role | You inherit risk you cannot control | Permanent only if formally assigned | Not Needed Yet
L4 Platform Administrator | Raise/track Now Support cases | Vendor escalation | Named customer contact / support entitlement | Escalations go nowhere | Permanent | Not Needed Yet

## Responsibility Modes
RESPONSIBILITY MODES - name which mode you are in before you accept a request. 'I can do X in Discovery/Troubleshooting mode; Configuration/Ownership needs Y.'
Mode | What It Means | Typical Activities | Authority Needed | Access Needed | What You Are NOT Agreeing To | Red-flag Phrase | Am I Operating In This Mode Today? (Y/N)
Discovery | Learning what exists and how it fits together; read-only. | Inventory, tracing, interviews, documenting | Access to observe; no authority to change | Read-only/inspect (L1-L2) | Fixes, outcomes, ownership | 'Just have a look at it'
Troubleshooting | Finding the cause of a specific issue; may recommend a fix. | Reproduce, read logs, isolate, report findings | Authority to investigate and escalate; not to change prod | Log/config read, sub-prod test (L2) | Making the fix; owning the outcome | 'Can you figure out why it's broken?'
Configuration | Making approved changes within defined scope. | Catalog/flow/rule edits, per change process | Authority within a defined scope and approved change | L3 in sub-prod; deploy per process | Platform-wide impact; production deployment unless stated | 'Can you just update that?'
Administration | Operating the application: users, groups, config, health. | Role assignment, monitoring, housekeeping | Authority over application operations | L3 plus agreed admin duties | Platform architecture, security policy | 'You're the admin now'
Ownership | Accountable for outcomes: availability, quality, risk acceptance. | Owning roadmap, decisions, risk | Decision rights and budget/priority influence | Whatever delivery needs, plus backup | Being blamed for pre-existing debt | 'It's yours now'
Production Support | Keeping live processes running; incident response. | Triage, workaround, escalate, restore | Defined response hours/SLAs; production authority or escalation | Production log/config access; break-glass process | 24x7 coverage unless agreed | 'Fix it now, whatever it takes'
Project Work | Planned changes with scope, time, testing, approval. | Requirements, build, test, release | Scope/schedule authority; change approval | Sub-prod build; release via process | Unscoped 'while you're in there' work | 'Small tweak, shouldn't take long'
Technical Leadership | Setting standards, architecture direction, mentoring. | Standards, reviews, decisions, onboarding | Authority to set/enforce standards | Broad read + review rights | Unfunded platform strategy | 'You know the most about it'
Note on E2: Lowest access level that lets you VERIFY this item. If you cannot verify it at your current access, leave Confidence at Low/Unknown and use this column as evidence for an access request.

## Transition Checklist
OWNERSHIP / TRANSITION CHECKLIST - get answers in writing (email is fine) BEFORE accepting ongoing ownership. 'Not Asked' items are your homework.
Category | Question To Ask | Evidence To Get | Status | Agreed Answer | Agreed With | Date | Notes
Responsibility | What exactly am I being asked to do (discovery / troubleshooting / configuration / ownership)? | Written scope in one or two sentences | Not Asked
Responsibility | Which applications/processes are in scope, and which are explicitly out of scope? | List of apps/processes | Not Asked
Responsibility | Am I responsible for outcomes, or for effort and reporting? | Wording agreed with manager | Not Asked
Responsibility | Is this in addition to my current job? What is deprioritized? | Capacity statement / priorities | Not Asked
Authority | What can I decide alone? What needs approval? | Decision rights list | Not Asked
Authority | Who is accountable if a change causes an incident? | Named person/role | Not Asked
Access | What access do I have today, and what is needed for the agreed scope? | Access Roadmap rows filled | Not Asked
Access | Who grants access and how long does it take? | Approver + SLA | Not Asked
Access | Is access permanent or temporary? Is it audited? | Agreement noted | Not Asked
Documentation | Does handoff documentation from the former admin exist? Where? | Location or 'none' | Not Asked
Documentation | Where will documentation live and who may edit it? | Location + standard | Not Asked
Documentation | Are there known undocumented customizations? | List or Unknown IDs | Not Asked
Backup / Support | Who is my backup administrator? | Name | Not Asked
Backup / Support | Is there a vendor/partner/Now Support contract? Who may open cases? | Contract + contacts | Not Asked
Backup / Support | Who can I ask technical questions during discovery? | Named SMEs | Not Asked
Escalation | Who do I escalate to for platform issues? for business decisions? | Escalation path | Not Asked
Escalation | What is the process when something breaks outside my scope? | Written process | Not Asked
Change Authority | Who approves changes to configuration? to production? | Approver per level | Not Asked
Change Authority | Is there a change process (CAB, tickets, update sets, pipeline)? | Process description | Not Asked
Production Access | Do I need production access? Read-only? Break-glass only? | Agreed model | Not Asked
Production Access | Who deploys to production? | Named role | Not Asked
Testing | Where do I test (sub-prod instance)? How fresh is it vs. production? | Instance + clone date | Not Asked
Testing | Who is responsible for UAT? Do automated tests exist? | Named responsibility | Not Asked
Approval | Who signs off on changes for each process? | Process owner list | Not Asked
Approval | What evidence of testing is required? | Checklist | Not Asked
Expected Outcomes | What does 'success' look like at 30, 60, 90 days? | Written outcomes | Not Asked
Expected Outcomes | Will performance be judged on discovery results or on fixing issues? | Written expectation | Not Asked
Timeline | What is the timeline for this transition? | Dates | Not Asked
Timeline | When is the next upgrade and who owns it? | Upgrade owner/date | Not Asked
Timeline | When will ownership/role be reviewed? | Review date | Not Asked
Something Is Broken | What is the business impact right now and who is affected? | Impact statement | Not Asked
Something Is Broken | Is there a runbook or past incident record? | Link or none | Not Asked
Something Is Broken | What can I do with my current access in a timeboxed investigation? | Investigation scope | Not Asked
Something Is Broken | Who approves a production change/workaround? | Approver | Not Asked
Something Is Broken | Who communicates status to the business? | Named person | Not Asked
Something Is Broken | What do I record afterward? (Unknown, Risk, Decision, Change) | Entries created | Not Asked

## Reference Lists
ObjectType | Status | ActiveInactive | OOTB | Criticality | DocStatus | Confidence | Access | Priority | Likelihood | Severity | RiskStatus | UnknownStatus | YesNoUnknown | Direction | Technology | Auth | Relationship | DepType | DecisionStatus | DecisionOrigin | ChangeResult | PlanStatus | ScriptType | FlowType | SecType | ACLOp | FieldType | ReqStatus | TempPerm | ChecklistStatus | Level | Env | Definitions
Table | In Use | Active | OOTB | Critical | Not Started | High | Basic User | Critical | Low | Low | Suspected | Open | Yes | Inbound | REST | Basic | reads from | Data | Proposed | New decision | Pending | Not Started | Business Rule | Flow | Role | read | String | Not Needed Yet | Temporary | Not Asked | L1 Discovery | Production | CONFIDENCE: High = verified directly in ServiceNow ¦ Medium = strongly supported, not fully verified ¦ Low = inferred, needs validation ¦ Unknown = not checked
Field | Not In Use | Inactive | Customized OOTB | High | Discovered | Medium | Elevated Application | High | Medium | Medium | Open | Investigating | No | Outbound | SOAP | OAuth 2.0 | writes to | Automation | Approved | Reconstructed (inferred) | Success | In Progress | Client Script | Subflow | Group | write | Integer | Planned | Permanent | Asked | L2 Application Analyst | Sub-production | CRITICALITY: Critical = process stops or compliance impact ¦ High = major degradation ¦ Medium = workaround exists ¦ Low = minor
Application | Unknown | Unknown | Custom | Medium | Partially Documented | Low | Admin | Medium | High | High | Mitigating | Blocked - Needs Access | Unknown | Bidirectional | Import Set / Transform Map | API Key | updates | Code | Implemented | Reconstructed (confirmed by SME) | Partial | Done | Script Include | Flow Action | ACL | create | Boolean | Requested | Temporary then review | Agreed | L3 Application Administrator | Both | RISK SCORE: Likelihood Low/Med/High = 1/2/3 times Severity Low/Med/High/Critical = 1/2/3/4. >=9 Critical, 6-8 High, 3-5 Medium, 1-2 Low
Module | Deprecated |  | Unknown | Low | Documented | Unknown | Security Admin | Low |  | Critical | Accepted | Blocked - Needs SME |  | Unknown | MID Server | Certificate / mTLS | creates records in | Security | Superseded |  | Failed | Skipped | UI Action | Scheduled Flow |  | delete | Choice | Granted | Either | Partially Agreed | L4 Platform Administrator | Unknown | DOC STATUS: Documented = template complete. Validated = confirmed by direct check or SME. Dashboard counts both as documented.
Flow | Planned |  |  | Unknown | Validated |  | Database/Platform |  |  |  | Closed | Resolved |  |  | IntegrationHub / Spoke | SSO / SAML | deletes from | UI | Reversed |  | Rolled Back | Blocked | UI Script | Legacy Workflow |  | execute | Reference | Denied |  | Declined |  |  | ACCESS NEEDED: Basic User < Elevated Application < Admin < Security Admin < Database/Platform. Pick the LOWEST level that lets you verify the item.
Subflow |  |  |  |  | Needs Update | [6 empty] | Closed - Not Resolvable |  |  | Email | None | runs on | Integration |  |  |  |  | Scheduled Script | Other |  | report_view | List | Granted - Temporary |  | Not Applicable |  |  | EXAMPLES: Rows with IDs starting EX- are fictional and excluded from Dashboard counts. Delete them when you are comfortable.
Flow Action | [14 empty] | SFTP / Flat File | Unknown | launches | Reporting |  |  |  |  | Fix Script |  |  | other | Glide Date/Time | [5 empty] | TO ADD A DROPDOWN VALUE: type it at the bottom of the list column (the dropdown range is fixed to the current length; insert a row INSIDE the list to extend it).
Business Rule | [14 empty] | JDBC |  | calls | Configuration |  |  |  |  | Script Action |  |  |  | Date
Client Script | [14 empty] | SSO / SAML / LDAP |  | called by | Notification |  |  |  |  | Scripted REST |  |  |  | Journal
UI Policy | [14 empty] | Other |  | triggers | Other |  |  |  |  | Transform Script |  |  |  | Script
UI Action | [14 empty] | Unknown |  | protects | [5 empty] | ACL Script |  |  |  | Currency
Script Include | [16 empty] | requires role | [5 empty] | Other |  |  |  | Other
ACL | [16 empty] | notifies
Role | [16 empty] | requests approval from
Group | [16 empty] | extends
Catalog Item | [16 empty] | references
Variable | [16 empty] | imports into
Variable Set | [16 empty] | exports from
Record Producer | [16 empty] | reports on
Notification | [16 empty] | displays
Scheduled Job | [16 empty] | member of
Integration | [16 empty] | depends on
REST API | [16 empty] | other
Data Source
Transform Map
Report
Dashboard
Widget
Portal
Knowledge Base
Other